## Gantt Chart
Room Tenant System
-
-
GROUP 4 | PROJECT LEAD |  |  | 2023-10-23 |  |  |  |  | 2023-10-30 |  |  |  |  | 2023-11-06 |  |  |  |  | 2023-11-13 |  |  |  |  | 2023-11-20 |  |  |  |  | 2023-11-27 |  |  |  |  | 2023-12-04 |  |  |  |  | 2023-12-11 |  |  |  |  | 2023-12-18 |  |  |  |  | 2023-12-25 |  |  |  |  | 2024-01-01 |  |  |  |  | 2024-01-08 |  |  |  |  | 2024-01-15 |  |  |  |  | 2024-01-22 |  |  |  |  | 2024-01-29 |  |  |  |  | -
| Dicha Zelianivan Arkana | [77 empty] | -
TASK |  | START | END | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | -
|  |  |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | -
INITIATION | bar: -
Define Project Scope |  | 2023-10-25 | 2023-10-26 | bar: W to T; -
Conduct Stakeholder Analysis |  | 2023-10-27 | 2023-10-28 | bar: F to M; -
Develop Project Charter |  | 2023-10-29 | 2023-10-30 | bar: T to W; -
Identify Project Team |  | 2023-10-31 | 2023-10-31 | bar: T; -
Perform Risk Assessment |  | 2023-11-01 | 2023-11-02 | bar: F to M; -
Define Project Objectives |  | 2023-11-03 | 2023-11-03 | bar: T; -
Create Project Schedule |  | 2023-11-04 | 2023-11-04 | bar: W; -
Obtain Project Approval |  | 2023-11-05 | 2023-11-05 | bar: T; -
PLAN | bar: -
Create Work Breakdown Structure |  | 2023-11-06 | 2023-11-07 | bar: F to M; -
Define Task Dependencies |  | 2023-11-08 | 2023-11-08 | bar: T; -
Develop Resource Management Plan |  | 2023-11-09 | 2023-11-10 | bar: W to T; -
Develop Project Schedule |  | 2023-11-11 | 2023-11-13 | bar: F to T; -
Conduct Risk Assessment and Mitigation Planning |  | 2023-11-14 | 2023-11-15 | bar: W to T; -
Finalize Project Budget |  | 2023-11-16 | 2023-11-17 | bar: F to M; -
Review and Refine Project Plan |  | 2023-11-18 | 2023-11-18 | bar: T; -
EXECUTE | bar: -
Develop User Interface Design |  | 2023-11-19 | 2023-11-23 | bar: W to T; -
Implement User Registration and Login |  | 2023-11-24 | 2023-11-26 | bar: W to F; -
Create Database Schema |  | 2023-11-27 | 2023-11-28 | bar: M to T; -
Develop Room Listing Functionality |  | 2023-11-29 | 2023-12-02 | bar: W to M; -
Develop Room Check-In and Check-Out Process |  | 2023-12-03 | 2023-12-06 | bar: T to F; -
Enable Room Availability Tracking |  | 2023-12-07 | 2023-12-09 | bar: M to W; -
Test and Debug System Functionality |  | 2023-12-10 | 2023-12-14 | bar: T to W; -
Perform User Acceptance Testing (UAT) |  | 2023-12-15 | 2023-12-17 | bar: T to M; -
Deploy System to Production Environment |  | 2023-12-18 | 2023-12-19 | bar: T to W; -
CONTROL | bar: -
Conduct Regular System Maintenance |  | 2023-12-20 | 2023-12-21 | bar: T to F; -
Perform Data Backup and Recovery |  | 2023-12-22 | 2023-12-22 | bar: M; -
Update and Maintain System Documentation |  | 2023-12-23 | 2023-12-23 | bar: T; -
Conduct Periodic Security Audits |  | 2023-12-24 | 2023-12-25 | bar: W to T; -
Conduct System Updates and Upgrades |  | 2023-12-26 | 2023-12-27 | bar: F to M; -
CLOSE | bar: -
Perform Final System Testing and Validation |  | 2023-12-28 | 2023-12-29 | bar: T to W; -
Complete User Acceptance Testing (UAT) |  | 2023-12-30 | 2023-12-31 | bar: T to F; -
Obtain Sign-Off and Acceptance from Stakeholders |  | 2024-01-01 | 2024-01-01 | bar: M; -
Perform Project Financial Closure |  | 2024-01-02 | 2024-01-02 | bar: T; -
Finalize and Close Contracts with Vendors |  | 2024-01-03 | 2024-01-03 | bar: W; -
Transfer Ownership of System and Assets |  | 2024-01-05 | 2024-01-05 | bar: T; -
Conduct Project Team Evaluation |  | 2024-01-05 | 2024-01-05 | bar: M to -

## Cost Estimate
WBS Items | Unit/Days | Cost/Unit/Days | Subtotal
1. Personnel Costs |  |  | 107675000
Project Manager | 73 | 325000 | 23725000
Developers | 146 | 300000 | 43800000
UI/UX Designer | 73 | 250000 | 18250000
Quality Assurance/Testers | 146 | 150000 | 21900000
2. Hardware, Software, and Licensing Costs |  |  | 8120000
Hardware | 1 | 8000000 | 8000000
Deployment and Hosting | 1 | 120000 | 120000
3. Discretionary Expenses (20% of est. expenses) |  |  | 23160000
Total Project Cost Estimate |  |  | 138955000